## Issues
Item # | Status | Associated Design Entity | Brief Description | Resource | Date identified | Date of last update | Plan date to resolve | Status of resolution / comments | Issue Type
1 | Resolved | Database | Installing mySQL | mySQL | 2018-01-23 | 2018-01-30 | 2018-01-25 | Switched to Firebase | Software
2 | Resolved | Installing NodeJS | Install NodeJS to each members device | NodeJS | 2018-01-23 | 2018-01-25 | 2018-01-25 | Resolved | Software
3 | Resolved | NodeJS | Learning to use NodeJS | NodeJS | 2018-01-16 | 2018-02-06 | Febuary 1, 2018 | Studying NodeJS | Software
4 | Resolved | mySQL | mySQL was inefficient to sort arrays | mySQL | 2018-01-17 | N/A | N/A | Unresolved due to software issues | Software
5 | Resolved | NodeJS | Unable to render asynchronous MySQL query results onto NodeJS page | NodeJS | 2018-01-26 | 2018-01-26 | 2018-01-26 | Resolved using express and pug | Software
6 | Resolved | Database | Configure Firebase | Firebase | 2018-01-30 | 2018-02-06 | 2018-01-31 | Currently finished | Software
7 | In progress | Database/NodeJS | User Registration | NodeJS | 2018-01-30 | 2018-02-21 | 2018-02-08 | Using nodeJS | Software
8 | In progress | Database/NodeJS | User Login | NodeJS | 2018-01-30 | 2018-02-21 | 2018-02-08 | Using nodeJS | Software
9 | In progress | Database/NodeJS | Sort / Filter Event (Form) | Firebase | 2018-01-30 | 2018-02-21 | 2018-02-08 | Being Resolved in Firebase | Software
10 | Resolved | Frontend | Convert HTML to PUG | NodeJS | 2018-01-30 | 2018-02-06 |  |  | Software
11 | Resolved | Database | Data not updating on new value | Firebase | 2018-02-01 | 2018-02-06 |  | Get a new snapshot, or update on 'value' | Software
12 | Resolved | NodeJS | Form data not submitting | Firebase | 2018-02-06 |  |  | Use of AJAX instead | Software
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Meta
Status | Issue Type
New | I: Issue
In progress | A: Action Item
Complete